## Sheet1
Sprints | Duration | User Stories | Task | Owner | Priority
Sprint 1 | 3 Weeks | #1 Cart Item Removal (High) #6 Clear Discounts (Medium) #7 Return & Shipping Policies Visibility (Medium) | • Design and implement visible remove buttons in cart & mini-cart • Update price display format to show old price, new price, discount % • Add “Undo” removal option • Add return & shipping policy links on product and checkout pages • Implement popup view for policies | Frontend Dev, UI/UX Designer | High / Medium
Sprint 2 | 2 Weeks | #2 High-Resolution Images with Zoom (High) #5 Trusted Payment Logos (High) | • Replace low-res images with 1080p versions • Implement zoom for desktop and mobile • Add Visa, MasterCard, PayPal logos in checkout • Add SSL security badge in checkout page | Frontend Dev, UI/UX Designer | High
Sprint 3 | 1 Month | #3 Shorter Checkout Process (High) #4 Faster Website Performance (High) | • Redesign checkout 3 steps • Add progress bar for checkout • Optimize images & enable lazy loading • Minimize unused CSS/JS • Test page load time and aim for ≤ 3 seconds | Frontend Dev, Backend Dev, UI/UX Designer | High